## Sneha
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot
1 | Lead | Create Lead | Medium | Ext Number is not displayed in Lead Detail page. | All Browsers
2 | Lead | Email Opt Out | High | Email Opt out feature not functioning correctly. Create Lead > Fill all required fields > Email Opt out > True > Save > Edit > Save>Email opt out becomes false | All Browsers
3 | Lead | Merge Leads | Medium | Lead >> Find Duplicates >> "Merge Leads" functionality is working but not displaying correct data. | All Browsers
4 | Lead | Open Activities | Low | Reminder heading should be present below near date and time selection. | All Browsers
5 | Lead | Open Activities | Medium | "Related to" is not allowing entry of any data. | All Browsers
6 | Lead | Open Activities | High | Open Activities >> Edit >>Save > It stays on same screen. | All Browsers
7 | Lead | Activity History | High | when "Assigned To" is changed then the activity does not save the changes | All Browsers
8 | Lead | Activity History | Low | Save and Cancel button should be only at the bottom right of page and not at the top. | All Browsers
9 | Lead | Open Activities | High | New Task is not getting created | Edge,Internet Explorer
10 | Lead | Activity History | High | Edit functionality not working. | Edge,Internet Explorer
11 | Lead | Lead List | Low | Email column overridding Company | Edge,Internet Explorer
12 | Lead | Lead List | Low | Company overlapping Lead Status | Edge,Internet Explorer
13 | Lead | Create Lead | Low | Salutation, Lead Source,Lead Status,Industry are autofilled when user clicks on create lead. | Internet Explorer
14 | Lead | UI > Lead Detail Page | Low | More space in view lead screen
Date: 05/23/2019
1 | Missing lead : A Lead of mine named Alan Coursey with State National is missing from the new CRM. | Working as expected
https://crm.chetu.com/lead/view-lead/00Q1T00001NjTe1UAF Coursey, Alan ----- Patrick Thompson
2 | On account Premier Pharmacy data shows only up to date 5/9/19 and for account Mediscan data show only up to 12/27/18. | Working as expected
3 | Snap engage Items. Configured | Reopened
4 | Need ability to Change Owners (only to ET team) | 1) It is implemented on Account and Lead only
2) At present it is visible to all types of users
5 | You should not be able to add Contact if the ‘Account Name’ is not selected | Working as expected
6 | Format of Date and Time (HH:MM:SS)-- | Reopened
1) Reports - do not show time in HH:MM:SS and have AM PM

## Rama
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot link
1 | Account | New account add | High | Account is saved without giving name(Just give space) | All Browsers | https://www.screencast.com/t/WdjxBoHot
2 | Account | New account add | Medium | Phone number should appear same way in entire column(it should be separate) | All Browsers | https://www.screencast.com/t/FU3R9STGmkUq
3 | Account | New account add | Medium | No validation for Zipcode,State country(It should not allow special char) | All Browsers | https://www.screencast.com/t/jek1wD3hPt
4 | Account | View account -> contact add | Medium | Addedd contacts are not dispalying under view account, contact list | All Browsers
5 | Account | New account add | Low | Industry drop down is not displaying properly | All Browsers | https://www.screencast.com/t/aoGgtvpON7W
6 | Account | New task add | High | Nothing happens by hit on save on new task add | Edge | https://www.screencast.com/t/1EYpkrcB3
7 | Account | Edit activity | HIgh | After edit save the activity then data is not saving | Edge
8 | Account | View user | Low | screen is not having to go back from view user screen | All Browsers | https://www.screencast.com/t/y5PPporh
9 | Contact | Create contact-> search account name | Low | after hit on name from lookup screen then screen redirect to previous screen | All browsers | https://www.screencast.com/t/N8oleaWTBm
10 | Contact | Create contact | Medium | Last name field should not allow special and numeric characters | All browsers | https://www.screencast.com/t/kZVkOnDv
11 | Contact | View contact | Low | Salutation missing on view contact screen | All browsers | https://www.screencast.com/t/zDBf7zCX
12 | Contact | Add contact | High | No validation for Email field | All browsers | https://www.screencast.com/t/sxaerwLgfpD1
13 | Contact | Create contact | High | contact is saved without giving name(Just give space) | All browsers | https://www.screencast.com/t/nJqW3bzpJJT
14 | Contact | Create contact | Medium | application Should not allow to give future birth date | All browsers | https://www.screencast.com/t/sN7I3k2sFGm
15 | Contact | Vew contact --> Add task | High | Task is saved without giving Subject(Just give space) | All browsers | https://www.screencast.com/t/J1DIvoYaB
16 | Contact | Vew contact --> edit task | Medium | Grid name is coming incorrectly(Here I am adding new task) | All browsers | https://www.screencast.com/t/854gOcUwgc
17 | Contact | Edit task --> Update | Medium | After task update then screen should redirct ot list screen | All Browsers | https://www.screencast.com/t/3yyTrp3fKf
18 | Contact | Vew contact--> Log activity | Low | By opening the log activity screen then ScheduleFollowUp task ashould be expand | All Browsers | https://www.screencast.com/t/yWWTYuz1byD
19 | Contact | Vew contact--> Log activity | High | Log activity is saved without giving Subject(Just give space) | All Browsers | https://www.screencast.com/t/PjPs3fD4W
20 | Contact | Vew contact--> Log activity | Medium | Duplicate Save and cancel buttons are appearing. | All Browsers | https://www.screencast.com/t/7GJ17RHk
21 | Contact | Vew contact--> Log activity | Low | As per suggestion chage text on ScheduleFollowUp screen | All Browsers | https://www.screencast.com/t/ydY4SbwX0qs8
22 | Contact | Vew contact-->Edit Log activity | Medium | After edit save the activity then screen should redirct to previous screen | All Browsers | https://www.screencast.com/t/nVnbldDt
23 | Contact | Vew contact-->Notes | High | Notes is saved without giving Title(Just give space and save) | All Browsers | https://www.screencast.com/t/cEliKkBaDL
24 | Contact | View contact--> notes->Delete | High | As per suggestion screen does not have deelte option | All Browsers | https://www.screencast.com/t/mmkv7Qcwd
25 | Contact | Vew contact-->new Notes | Medium | After add new notes then screen should redirect to list view contact screen | All Browsers | https://www.screencast.com/t/o4qkRr9gaXZ
26 | Contact | View contact --> attachments | High | Save button functionality not working | All Browsers
Date: 05/23/2019
27 | Leads and contact |  | High | 2nd name of Lead and contact module is not coming as per modules | All browsers | https://www.screencast.com/t/Nh1ZmCGRrq
28 | Leads |  | Medium | Website filed should appear like link | All browsers | https://www.screencast.com/t/X4JGfQk5DFOW
29 | Dashboard |  | Low | Notifications bell icon count is appearing properly | All browsers | https://www.screencast.com/t/B02KqE12Y3b
30 | Any module |  | Medium | Module selection is not highlighting (In view screen any module) | All browsers | https://www.screencast.com/t/b0FavWK3C889
31 | Opportunity |  |  | Amount field should not allow alphabets and special char | All browsers | https://www.screencast.com/t/3I5XHWbX

## Deepender
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot link
1 | Opportunity | New Opportunity | Medium | Close date field accepting by default value from server and also editable | All browsers | https://imgur.com/KFNgtyN
2 | Opportunity | New Opportunity | Low | Number of by default fields are not same in different browsers | All browsers | https://imgur.com/Cr2aTD7
3 | Opportunity | New Opportunity | Low | Spacing issue in error message | All browsers | https://imgur.com/poJVZ4g
4 | Opportunity | New Opportunity | Medium | Search symbol in Account name field changing its location | All browsers | https://imgur.com/mBkblDy
5 | Opportunity | New Opportunity | Medium | in account name field Lookup window not hiding after selecting particular name | All browsers | https://imgur.com/AStj82d
6 | Opportunity | New Opportunity | Low | Drop down list should contain "select" as by default | All browsers | https://imgur.com/wgn7E30
7 | Opportunity | New Opportunity | High | Unnecessary error is coming while saving the record | In Edge and IE browser | https://imgur.com/7pHfGeB
8 | Opportunity | New Opportunity | High | new opportunity page is not redirecting to the view opportunity after saving | In Edge and IE browser | https://imgur.com/ILsNGOV
9 | Opportunity | View Opportunity-New task | Low | extra space | All browsers | https://imgur.com/bo5ngde
10 | Opportunity | View Opportunity-New task-Open Activities | High | Tasks are not coming in Open activity list after adding new task | All browsers | https://imgur.com/ErrRoez
11 | Opportunity | View Opportunity | Suggestion | Follow the screenshot link | All browsers | https://imgur.com/JYOCmag
12 | Opportunity | View Opportunity-New task | High | Email field is not working | All browsers | https://imgur.com/gWck22A
13 | Opportunity | View Opportunity-New task | Low | unnecessary field is comming | All browsers | https://imgur.com/2zKrZue
14 | Opportunity | View Opportunity-Activity history-Log activity | Low | unnecessary field is coming | All browsers | https://imgur.com/Q81r1aT
15 | Opportunity | View Opportunity-Activity history-Log activity | High | Email field is not working | All browsers | https://imgur.com/W4rLldJ
16 | Opportunity | View Opportunity-Activity history-Log activity | High | Tasks are not coming in activity history list after adding sechdeule task | All browsers | https://imgur.com/JVelsVa
17 | Opportunity | View Opportunity-Activity history-Log activity | Suggestion | Follow the screenshot link | All browsers | https://imgur.com/W4rLldJ
18 | Opportunity | View Opportunity-Activity history-Log activity | Major Suggestion | Follow the screenshot link | All browsers | https://imgur.com/E10V6hY
Note: As suggested, I have only done the Functionality testing.
Date: 05/23/2019
19 | Opportunity | Opportunity List | Medium | Paging functinality is not giving the desired result | All browsers | https://imgur.com/99gnQJ8
20 | Opportunity | Opportunity List | Medium | Sorting functionality is not working correctly | All browsers | https://imgur.com/jeBylzc
21 | Opportunity | View Opportunity-New task | high | Field is blocked | All browsers | https://imgur.com/ZGe9qIY
22 | Opportunity | New Opportunity | low | Labeling is not correct | All browsers | https://imgur.com/5Nr6JtQ
23 | Opportunity | View Opportunity-New task | low | Labeling is missing | All browsers | https://imgur.com/tvAx49K