## Sneha
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot
1 | Lead | Create Lead | Medium | Ext Number is not displayed in Lead Detail page. | All Browsers
2 | Lead | Email Opt Out | High | Email Opt out feature not functioning correctly. Create Lead > Fill all required fields > Email Opt out > True > Save > Edit > Save>Email opt out becomes false | All Browsers
3 | Lead | Merge Leads | Medium | Lead >> Find Duplicates >> "Merge Leads" functionality is working but not displaying correct data. | All Browsers
4 | Lead | Open Activities | Low | Reminder heading should be present below near date and time selection. | All Browsers
5 | Lead | Open Activities | Medium | "Related to" is not allowing entry of any data. | All Browsers
6 | Lead | Open Activities | High | Open Activities >> Edit >>Save > It stays on same screen. | All Browsers
7 | Lead | Activity History | High | when "Assigned To" is changed then the activity does not save the changes | All Browsers
8 | Lead | Activity History | Low | Save and Cancel button should be only at the bottom right of page and not at the top. | All Browsers
9 | Lead | Open Activities | High | New Task is not getting created | Edge,Internet Explorer
10 | Lead | Activity History | High | Edit functionality not working. | Edge,Internet Explorer
11 | Lead | Lead List | Low | Email column overridding Company | Edge,Internet Explorer
12 | Lead | Lead List | Low | Company overlapping Lead Status | Edge,Internet Explorer
13 | Lead | Create Lead | Low | Salutation, Lead Source,Lead Status,Industry are autofilled when user clicks on create lead. | Internet Explorer
14 | Lead | UI > Lead Detail Page | Low | More space in view lead screen
Date: 05/23/2019
15 | Missing lead : A Lead of mine named Alan Coursey with State National is missing from the new CRM. | Working as expected
https://crm.chetu.com/lead/view-lead/00Q1T00001NjTe1UAF Coursey, Alan ----- Patrick Thompson
16 | On account Premier Pharmacy data shows only up to date 5/9/19 and for account Mediscan data show only up to 12/27/18. | Working as expected
17 | Snap engage Items. Configured | Reopened
18 | Need ability to Change Owners (only to ET team) | 1) It is implemented on Account and Lead only
2) At present it is visible to all types of users
19 | You should not be able to add Contact if the ‘Account Name’ is not selected | Working as expected
20 | Format of Date and Time (HH:MM:SS)-- | Reopened
1) Reports - do not show time in HH:MM:SS and have AM PM
Date: 05/24/2019
8 Issues Retested and sent email to Client. ( Sheet 2 contains the issues retested)
66 Issues verified and updated in spreadsheet.( I have marked the date)
Date: 05/27/2019
21 | On account Premier Pharmacy data shows only+B36:B46 up to date 5/9/19 and for account Mediscan data show only up to 12/27/18. |  | Working as expected
22 | Missing lead : A Lead of mine named Alan Coursey with State National is missing from the new CRM |  | Working as expected
23 | Remove all gray borders |  | Working as expected
24 | Activity Type as 'Email' in plugin |  | Need outlook plugin
25 | convert Lead to Account |  | Working as expected
26 | Report can have same name if in different folder Public/Private |  | Working as expected
27 | Remove Export Button from Reports |  | Working as expected
28 | Removing Cancel and Save button from bottom of 'Email' Activity Type |  | Working as expected
29 | Delete All Public reports created by Sales people |  | Working as expected
30 | Event Import in database |  | Need UI to verify
31 | Pick list- remove Add New and edit |  | Need Setup module
32 | check auto syncing, activity type 'email' not saving, email not populating on manual sync |  | Need outlook plugin
33 | Note Display on UI |  | High | 1) Related To field displays nothing. 2) Wrong date is getting displayed. 3) Created by displays nothing.
34 | Report : Leads By Lead Source(specific Show |  | HIgh | 1) Wrong Name in “created by” column. 2) Wrong Date in “created by” column. 3) Wrong date in “Open Activities”. 4) “Assigned to” missing in Activity History. 5) Phone field does not get displayed in Activity History. Please refer the attachment.
Date: 05/28/2019
Verified & Updated 61 issues in spreadsheet
Verified Snap Engage functionality

## Rama
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot link
1 | Account | New account add | High | Account is saved without giving name(Just give space) | All Browsers | https://www.screencast.com/t/WdjxBoHot
2 | Account | New account add | Medium | Phone number should appear same way in entire column(it should be separate) | All Browsers | https://www.screencast.com/t/FU3R9STGmkUq
3 | Account | New account add | Medium | No validation for Zipcode,State country(It should not allow special char) | All Browsers | https://www.screencast.com/t/jek1wD3hPt
4 | Account | View account -> contact add | Medium | Addedd contacts are not dispalying under view account, contact list | All Browsers
5 | Account | New account add | Low | Industry drop down is not displaying properly | All Browsers | https://www.screencast.com/t/aoGgtvpON7W
6 | Account | New task add | High | Nothing happens by hit on save on new task add | Edge | https://www.screencast.com/t/1EYpkrcB3
7 | Account | Edit activity | HIgh | After edit save the activity then data is not saving | Edge
8 | Account | View user | Low | screen is not having to go back from view user screen | All Browsers | https://www.screencast.com/t/y5PPporh
9 | Contact | Create contact-> search account name | Low | after hit on name from lookup screen then screen redirect to previous screen | All browsers | https://www.screencast.com/t/N8oleaWTBm
10 | Contact | Create contact | Medium | Last name field should not allow special and numeric characters | All browsers | https://www.screencast.com/t/kZVkOnDv
11 | Contact | View contact | Low | Salutation missing on view contact screen | All browsers | https://www.screencast.com/t/zDBf7zCX
12 | Contact | Add contact | High | No validation for Email field | All browsers | https://www.screencast.com/t/sxaerwLgfpD1
13 | Contact | Create contact | High | contact is saved without giving name(Just give space) | All browsers | https://www.screencast.com/t/nJqW3bzpJJT
14 | Contact | Create contact | Medium | application Should not allow to give future birth date | All browsers | https://www.screencast.com/t/sN7I3k2sFGm
15 | Contact | Vew contact --> Add task | High | Task is saved without giving Subject(Just give space) | All browsers | https://www.screencast.com/t/J1DIvoYaB
16 | Contact | Vew contact --> edit task | Medium | Grid name is coming incorrectly(Here I am adding new task) | All browsers | https://www.screencast.com/t/854gOcUwgc
17 | Contact | Edit task --> Update | Medium | After task update then screen should redirct ot list screen | All Browsers | https://www.screencast.com/t/3yyTrp3fKf
18 | Contact | Vew contact--> Log activity | Low | By opening the log activity screen then ScheduleFollowUp task ashould be expand | All Browsers | https://www.screencast.com/t/yWWTYuz1byD
19 | Contact | Vew contact--> Log activity | High | Log activity is saved without giving Subject(Just give space) | All Browsers | https://www.screencast.com/t/PjPs3fD4W
20 | Contact | Vew contact--> Log activity | Medium | Duplicate Save and cancel buttons are appearing. | All Browsers | https://www.screencast.com/t/7GJ17RHk
21 | Contact | Vew contact--> Log activity | Low | As per suggestion chage text on ScheduleFollowUp screen | All Browsers | https://www.screencast.com/t/ydY4SbwX0qs8
22 | Contact | Vew contact-->Edit Log activity | Medium | After edit save the activity then screen should redirct to previous screen | All Browsers | https://www.screencast.com/t/nVnbldDt
23 | Contact | Vew contact-->Notes | High | Notes is saved without giving Title(Just give space and save) | All Browsers | https://www.screencast.com/t/cEliKkBaDL
24 | Contact | View contact--> notes->Delete | High | As per suggestion screen does not have deelte option | All Browsers | https://www.screencast.com/t/mmkv7Qcwd
25 | Contact | Vew contact-->new Notes | Medium | After add new notes then screen should redirect to list view contact screen | All Browsers | https://www.screencast.com/t/o4qkRr9gaXZ
26 | Contact | View contact --> attachments | High | Save button functionality not working | All Browsers
Date: 05/23/2019
27 | Leads and contact |  | High | 2nd name of Lead and contact module is not coming as per modules | All browsers | https://www.screencast.com/t/Nh1ZmCGRrq
28 | Leads |  | Medium | Website filed should appear like link | All browsers | https://www.screencast.com/t/X4JGfQk5DFOW
29 | Dashboard |  | Low | Notifications bell icon count is appearing properly | All browsers | https://www.screencast.com/t/B02KqE12Y3b
30 | Any module |  | Medium | Module selection is not highlighting (In view screen any module) | All browsers | https://www.screencast.com/t/b0FavWK3C889
31 | Opportunity |  |  | Amount field should not allow alphabets and special char | All browsers | https://www.screencast.com/t/3I5XHWbX
Date: 05/24/2019
32 | Reports |  | Medium | Opportunity Status column is not appearing (even if I select from select columns list) | All browsers
33 | Reports |  | Low | Number of resources name is not appearing properly in pop up scree(text is coming out of the pop up) | All browsers | https://www.screencast.com/t/kjn8DudPO
34 | Reports |  | High | All columns are not appearing in screen(If I select all columns). | All browsers
35 | Reports |  | High | Getting spinner wheel appearing, If I create new report and edit on same record | All browsers
Date: 05/27/2019
36 | Task Email/Comment: Make Full Height, Work on read only and edit. |  | High | Reopened(Still Comment is editable if activity type is Email) Comment.Png
37 | Task Page UI Issue |  | High | UI looks good But getting below issues in task 1.After editand save the Task,screen should redirect to previous screen. 2.Task is Saving, without giving subject name 3.EDGE Browser : Task is not Saving
38 | Need ability to Change Owners on account |  | NA | As discussion with Dev. Team Sales ppt user doesnot have permisson to change the owners on account.so here need ET account
39 | Sorting of Lead Source |  | Medium | Lead source date(DD-MM-YYYY) is not sorting properly.
40 | Snap Engage - if lead or contact already exist then create task |  | NA | Functionality is still In development
41 | Task list with Filter |  | NA | Need discussion
Date: 05/28/2019
No tasks assigned today

## Deepender
Issue ID | Module Name | Sub Module | Priority | Issue Description | Browser | Screenshot link
1 | Opportunity | New Opportunity | Medium | Close date field accepting by default value from server and also editable | All browsers | https://imgur.com/KFNgtyN
2 | Opportunity | New Opportunity | Low | Number of by default fields are not same in different browsers | All browsers | https://imgur.com/Cr2aTD7
3 | Opportunity | New Opportunity | Low | Spacing issue in error message | All browsers | https://imgur.com/poJVZ4g
4 | Opportunity | New Opportunity | Medium | Search symbol in Account name field changing its location | All browsers | https://imgur.com/mBkblDy
5 | Opportunity | New Opportunity | Medium | in account name field Lookup window not hiding after selecting particular name | All browsers | https://imgur.com/AStj82d
6 | Opportunity | New Opportunity | Low | Drop down list should contain "select" as by default | All browsers | https://imgur.com/wgn7E30
7 | Opportunity | New Opportunity | High | Unnecessary error is coming while saving the record | In Edge and IE browser | https://imgur.com/7pHfGeB
8 | Opportunity | New Opportunity | High | new opportunity page is not redirecting to the view opportunity after saving | In Edge and IE browser | https://imgur.com/ILsNGOV
9 | Opportunity | View Opportunity-New task | Low | extra space | All browsers | https://imgur.com/bo5ngde
10 | Opportunity | View Opportunity-New task-Open Activities | High | Tasks are not coming in Open activity list after adding new task | All browsers | https://imgur.com/ErrRoez
11 | Opportunity | View Opportunity | Suggestion | Follow the screenshot link | All browsers | https://imgur.com/JYOCmag
12 | Opportunity | View Opportunity-New task | High | Email field is not working | All browsers | https://imgur.com/gWck22A
13 | Opportunity | View Opportunity-New task | Low | unnecessary field is comming | All browsers | https://imgur.com/2zKrZue
14 | Opportunity | View Opportunity-Activity history-Log activity | Low | unnecessary field is coming | All browsers | https://imgur.com/Q81r1aT
15 | Opportunity | View Opportunity-Activity history-Log activity | High | Email field is not working | All browsers | https://imgur.com/W4rLldJ
16 | Opportunity | View Opportunity-Activity history-Log activity | High | Tasks are not coming in activity history list after adding sechdeule task | All browsers | https://imgur.com/JVelsVa
17 | Opportunity | View Opportunity-Activity history-Log activity | Suggestion | Follow the screenshot link | All browsers | https://imgur.com/W4rLldJ
18 | Opportunity | View Opportunity-Activity history-Log activity | Major Suggestion | Follow the screenshot link | All browsers | https://imgur.com/E10V6hY
Note: As suggested, I have only done the Functionality testing.
Date: 05/23/2019
19 | Opportunity | Opportunity List | Medium | Paging functinality is not giving the desired result | All browsers | https://imgur.com/99gnQJ8
20 | Opportunity | Opportunity List | Medium | Sorting functionality is not working correctly | All browsers | https://imgur.com/jeBylzc
21 | Opportunity | View Opportunity-New task | high | Field is blocked | All browsers | https://imgur.com/ZGe9qIY
22 | Opportunity | New Opportunity | low | Labeling is not correct | All browsers | https://imgur.com/5Nr6JtQ
23 | Opportunity | View Opportunity-New task | low | Labeling is missing | All browsers | https://imgur.com/tvAx49K
Date: 05/24/2019
As suggested, I have done testing on clickable feature for Opportunity List and no issue found at my end.
Date: 05/27/2019
24 |  | Create new reports: Chetu - Closing & Discovery Calls AB - Daily Activity Report [A-F] | High | • run report functionality is not working under opportunity report and Accounts report • Incorrect range is coming • No error message is coming if all fields are not field properly • Date should not be editable except custom • Sorting functionality is not working correctly
25 |  | Report needs to be scrollable to the right side. When you have too many columns, you should be able to slide right and see data in larger column width You can remove this ‘AND’. Done | Working as expected
26 |  | By default it needs to be disabled | Working as expected
27 |  | Task in Dashboard | Working as expected
28 |  | Edit on filter report | High | • Edit functionality is not available under report filters of creating new Activity report
29 |  | Show full name of Sales Person |  | • only first name is coming in salesperson name
30 |  | Issue not able to click contact on Lead report(example Marketing Funnel: Leads Copy) | Working as expected
31 |  | Activities addition by user on Account, Opportunity, Contact, Lead |  | • Not able to add new task for new opportunity created • View Opportunity- Activity History field is blocked
32 |  | View Opportunity- Activity History | Medium | • Position of buttons is incorrect
33 |  | View Opportunity-Open Activity | Medium | • Form is not redirecting to the correct location • Labeling is Incorrect • Labeling is missing
Date: 05/28/2019
no new issues found, but I have performed retesting on earlier logged issues and from them few issues has been fixed now