## Sheet1 (hidden)
[5 empty] | Documentation Due Date |  |  |  | Documentation Sent Date |  |  | Development |  |  |  | QA and Release |  |  | ETC |  |  | Management | [6 empty] | Environment Setup |  |  |  | Project Status
Project Name | Project Manager | Priority - 5 to 1 (5 being highest) | Last DO review done with PM | Project Start Date | HLD | HLD | DDD | PP/Tasklist | HLD | DDD | PP/Tasklist | Is Team On Schedule as per Project Plan? | Is Source Control (VSS/Subversion) Upto Date? | Daily Code Backup Taken? | Was QA Release Done by Development Team? | Was QA done by QA Team | Last Interim Release Done on? | Next Interim Release Due on? | Is Architecture Approved by ETC? | When was Last ETC Project Review Done? | Was ETC Help Required this Week? | Was Project Plan Updated? | Was Weekly Status Meeting Done? | Were Meeting Minutes Sent? | Were all 5:15s Sent to Client Daily? | Did Team Members Have to Stay Late? | Is PM Visit to Client Site Required Periodically | Last PM Visit (Date) | Development Machine is Setup Completely? | Staging Machine is Setup ? (Chetu) | QA/UAT Environment Setup? (Client) | Production Machine Setup (Client) | Overall Project Status (Green, Yellow or Red) | Date of Last Project Plan Sent | Project Plan uploaded on Backbone | is Production/Staging Access Available? | Project Keyword entered in backbone? | Last Account Approval Date | Comment
IosHealths-P1 |  |  |  | 3/22/2012 |  |  | NA | 2012-04-05 | NA | NA | 2012-04-06 |  |  | Y | N | [13 empty] | Y | N | N | N | Green | 2012-08-13 | Y |  | Y
IosHealths-P2 |  |  |  | 2012-03-27 |  |  | NA | 2012-04-06 | NA | NA | 2012-04-06 |  |  | Y | N | [13 empty] | Y | Y | Y | N | Rolled Off | 2012-07-06 | Y |  | NA
VircoEHR-QA |  |  | 2013-03-07 | [7 empty] | 2012-06-20 |  |  | NA | NA | [13 empty] | NA | N | Y | N | Green | 2012-12-21 | Y | N | Y | NA | copy task list to implementation folder, copy mom for ETL to Virco-HER
VircoEHR |  |  | 2013-01-02 | [10 empty] | Y | Y | [13 empty] | Y | N | Y | N | Green | 2013-03-07 | N | N | Y |  | Update start and end day and upload project plan on backbone.
Virco-LabTracker |  |  | 2013-01-02 | [10 empty] | Y | Y | [13 empty] | Y | N | Y | N | Green | 2013-03-07 | N | N | Y
IosHealths-Palig |  |  |  | 2012-04-17 |  |  | NA | 2012-04-24 | NA | NA | 2012-04-18 |  |  | NA | NA | [13 empty] | Y | N | Y | N | Rolled Off | 2012-05-30 | Y | N | NA
Janssen-AVIGA |  |  | 2013-01-02 | 2012-04-19 |  |  | 2012-04-26 | 2012-05-03 | 2012-06-01 |  | 2012-06-04 |  |  | NA | NA | [13 empty] | Y | Y | Y | N | Green | 2013-03-05 | Y | N | Y | 2013-03-07
VTM-Medical Content |  |  |  | 2012-04-20 |  |  | 2012-04-27 | 2012-05-04 | 2012-05-07 | 2012-05-25 | 2012-05-07 | [17 empty] | N | N | N | N | Green | 2012-09-24 | Y | Y | NA
NationsHealth |  |  | 2013-01-02 | 2012-05-08 |  |  | 2012-05-22 | 2012-05-22 | 2012-05-16 | 2012-06-04 | 2012-05-30 |  |  | NA | NA | [13 empty] | Y | Y | Y | Y | Green | 2013-03-07 | Y | N | Y | 2013-03-07
Iatric-Interface |  |  |  | 2012-06-19 |  |  | 2012-07-03 | 2012-06-26 | 2012-06-29 | 2012-07-03 | 2012-07-06 |  |  | Y | Y | [13 empty] | Y | Y | Y | Y | Green | 2012-08-09 | y |  | N
ParTech |  |  |  | 2012-07-13 |  |  |  | 2012-07-27 | 2012-07-27 |  |  |  |  | NA | NA | [13 empty] | Y | N | Y | N | Rolled Off |  | N | N | Y
Maverick-Web |  |  | 2013-01-02 | 2012-09-17 |  | 2012-09-25 | 2012-10-09 | 2012-10-02 | 2012-10-08 | 2012-10-28 | 2012-10-10 |  |  | Y | Y | [13 empty] | Y | Y | Y | Y | Green | 2013-02-27 | Y | N | Y | 2013-03-27
Maverick-IOS |  |  | 2013-01-02 | 2012-09-17 |  | 2012-09-25 | 2012-10-09 | 2012-10-02 | 2012-10-08 | 2012-10-27 | 2012-10-10 |  |  | Y | Y | [13 empty] | Y | Y | Y | Y | Green | 2013-03-07 | Y | N | Y | 2013-03-27
HPParteners-InfoNET |  |  | 2013-01-02 | 2012-10-05 |  | 2012-10-12 | 2012-10-19 | 2012-10-19 | 2012-10-24 | 2012-10-26 | 2012-11-07 |  |  | NA | NA | [13 empty] | Y | Y | Y | Y | Green | 2013-02-06 | Y | N | Y | 2013-03-28
HPParteners-GlobalNET |  |  | 2013-01-02 | 2012-10-05 |  | 2012-10-13 | 2012-10-20 | 2012-10-20 | 2012-10-24 | 2012-10-26 | 2012-11-26 |  |  | NA | NA | [13 empty] | Y | Y | Y | Y | Green | 2013-02-27 | Y | N | Y | 2013-03-29
HPPartners-SSRS |  |  | 2013-01-02 | 2012-10-05 |  | 2012-10-13 | 2012-10-20 | 2012-10-20 | 2012-10-24 | 2012-10-26 | 2012-11-05 |  |  | NA | NA | [13 empty] | Y | Y | Y | Y | Green | 2013-02-27 | Y | N | Y | 2013-03-30
Note on C2: souravh: To be set by DO in Review meet
Note on AU9: This is good until 02/15/2013.
Note on AU14: This is good untill 01/15/13.
Note on AU15: This is good untill 01/15/13.
Note on AU16: ashisha: 2/30/2013
Note on AU17: ashisha: 2/30/2013
Note on AU18: ashisha: 2/30/2013

## Sheet2
| Project Name | IosHealths-P1 | IosHealths-P2 | Tallowmasters-P1 | IosHealths-Palig | BuildingIntelligence-REAL | BuildingSolutionsProvider-CONT | CodeBox-REAL | Novup - FINT | CRM - Novup- FINT2 | CWIdea- FMRS | DelucaAndHartman-FMRS | ENGWorks- CONT | ForsetiRealEstateServices-REAL | MasterGraphicsAEC-CONT | PlanetPayment-FI
| Team Lead |  |  | Chetna Jain |  | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2 | Anil Singh2
| Priority - 5 to 1 (5 being highest) |  |  | 4
| Last FM review done with TL |  |  | 2013-03-21
| Project Start Date | 3/22/2012 | 2012-03-27 | 2012-11-01 |  | 2017-03-11 | 2019-03-09 | 2018-06-22 | 2018-09-05 | 2018-11-01 | 2018-10-10 | 2019-02-28 | 2018-10-08 | 2018-06-28 | 2018-06-18 | 2014-01-07
QA | Morning Snap Meeting Done? |  |  |  |  | Yes | New Project | Yes | Yes | Yes | Yes | New Project | Yes | Yes | Yes | Yes
| Test Plan uploaded on Backbone |  |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Test cases created for project |  |  |  |  | Yes | New Project | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Bugs are reported in backbone |  |  |  |  | Yes | New Project | Yes | Yes | Yes | Yes | New Project | No | Yes | Yes | Yes
| Bugs are reported in client tool | Y | Y | N |  | No | No | No | No | No | No | No | No | No | No | No
| QA release given to QA team. |  |  | TBD |  | Yes | New Project | Yes | Yes | Yes | Yes | New Project | Yes | Yes | Yes | Yes
| 5:15 to client |  |  | 2013-02-28 |  | No | No | No | No | No | No | No | No | No | No | No
|  | N | N | Y
QA and Release | Last Interim Release Done on? |  |  | 2013-03-21 |  | 2019-03-29 | New Project | 2019-04-02 | 2019-03-28 | 2019-03-29 | 2019-04-01 | New Project | 2019-03-14 | 2019-03-13 | 2019-03-23 | 2019-04-15
| Release Number? |  |  | 6 |  | Git: 105f288ef032cf43bb2efb27762f4798cc5dbb62 | New Project | 5 | 2.1 | 2.4 | 1.6 | New Project | 1.0.3.615684 | 2.3 | 1.0. 17.616598 | 2.7
| Next Interim Release Due on? |  |  | 2013-03-19 |  | Project Plan not updated | 2019-04-29 | Project Plan not updated | 2019-04-17 | 2019-04-18 | 2019-04-17 | 2019-04-18 | 2019-04-18 | Project Plan not updated | 2019-05-03 | Project Plan not updated
| Was QA done by QA Team |  |  | Y |  | Yes | New Project | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Management | Was Project Plan Updated? |  |  | Y |  | No | Yes | No | Yes | Yes | No | Yes | Yes | NO | Yes | No
| Was Weekly Status Meeting Done? |  |  | Y |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | yes | Yes | Yes
Y
Y
| Did Team Members Have to Stay Late? |  |  |  |  | No | No | No | No | No | No | No | No | No | No | No
| Planned/Unplanned leaves by team I last 1 month. |  |  | No |  | No | No | No | No | No | No | No | No | No | No | No
|  | Y | NA | Y
Documentation | Test plan updated | NA | NA | 2012-12-03 |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| HLD / DDD if applicable |  |  | Y |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Environment Setup |  | Y | Y | Y
| QA Environment Setup? (Chetu) | N | Y | N |  | Yes | New Project | Yes | Yes | Yes | Yes | New Project | Yes | No | Yes | Yes
| Staging/UAT Environment Setup? (Client) | N | Y | Y |  | No | New Project | Yes | Yes | Yes | No | New Project | No | Yes | No | No
|  | N | N | Y
N
| Overall Project Status (Green, Yellow or Red) | Green | Rolled Off | Good | Rolled Off | Green | Green | Green | Green | Green | Green | Green | Green | Green | Green | Green
Note on B3: To be set by FM in Review meet